## Sheet1
WBS | Task / Deliverable | Description | Due Date | Assigned To | Status
1 | Project Planning | Plan the project and organize the team work | 2026-09-03 | Team | In Progress
1.1 | Team Charter | Define project objective, roles, and meeting schedule | 2026-08-27 | Team | Complete
1.2 | System Vision | Defined project purpose and benefits, set up GitHub | 2026-08-30 | Team | Complete
1.3 | WBS & Project Plan | Create work breakdown plan and sturctured it | 2026-09-03 | Team | In Progress
1.4 | Project Scope Document | Define project boundaries and deliverables | 2026-09-06 | Team | Not Started
1.5 | Budget | Estimate the project budget | 2026-09-06 | Team | Not Started
2 | Requirements & Design | identify system requirements how project will works |  | Team | Not Started
2.1 | SRS | document system requirments | 2026-09-13 | Team | Not Started
2.2 | Project Pitch | Present the project idea | 2026-09-17 | Team | Not Started
2.3 | SDD | Documnet system and UI design | 2026-10-01 | Team | Not Started
3 | Development | Build the project application |  | Team | Not Started
3.1 | Proof of Concept | Create a video outlining the project's proof of concept and status | 2026-10-11 | Team | Not Started
3.2 | User Login & Registration | Design UI with user login and registration page |  | Darima / Musaib | Not Started
3.3 | Course Management | Design UI page with all registered courses |  | William | Not Started
3.4 | Assignment Management | Design UI to allow students to modify assignment information |  | Darima / Musaib | Not Started
3.5 | Assignment Status | Design UI with completion status for each individual assignment |  | Musaib | Not Started
3.6 | Upcoming Deadlines/UI | Design UI with assignment deadlines for each class |  | William | Not Started
3.7 | BETA Release & Code Walkthrough | Demo the application and release the beta in Github | 2026-11-22 | Team | Not Started
4 | Documentation & Testing | Document and test the application |  | Team | Not Started
4.1 | Technical Documentation | Prepare all technicals documentations | 2026-12-03 | Musaib / Team | Not Started
4.2 | Test Plan | Create test plan | 2026-12-10 | Team | Not Started
4.3 | Test Executions | Create test cases and execute them, record results | 2026-12-10 | Team | Not Started
4.4 | Bug Tracker | Track and manage bugs | 2026-12-10 | Darima | Not Started
4.5 | Issue Log | Log issues and resolve it | 2026-12-10 | Team | Not Started
5 | Final Release | Finalized and deliver the project | 2026-12-13 | Team | Not Started
5.1 | Release 1.0 | Official Release 1.0 of StudyBuddy | 2026-12-17 | Team | Not Started
5.2 | Final 1.0 Release Presentation | Prepare and deliver final presentation | 2026-12-17 | Team | Not Started
5.3 | Peer Review | Participate in the peer review