## Sheet1
WBS | Task / Deliverable | Due Date | Assigned To | Status
1 | Project Planning |  | Team | In Progress
1.1 | Team Charter | 2026-08-27 | Team | Complete
1.2 | System Vision | 2026-08-30 | Team | Complete
1.3 | WBS & Project Plan | 2026-09-03 | Darima /Willaim | In Progress
1.4 | Project Scope Document | 2026-09-06 | Team | Not Started
1.5 | Budget | 2026-09-06 | Team | Not Started
2 | Requirements & Design |  | Team | Not Started
2.1 | SRS | 2026-09-13 | Team | Not Started
2.2 | Project Pitch | 2026-09-17 | Team | Not Started
2.3 | SDD | 2026-10-01 | Team | Not Started
3 | Development |  | Team | Not Started
3.1 | Proof of Concept | 2026-10-11 | Team | Not Started
3.2 | User Login & Registration | Before Beta | Darima / Musaib | Not Started
3.3 | Course Management | Before Beta | William | Not Started
3.4 | Assignment Management | Before Beta | Darima / Musaib | Not Started
3.5 | Assignment Status | Before Beta | Musaib | Not Started
3.6 | Upcoming Deadlines/UI | Before Beta | William | Not Started
3.7 | BETA Release & Code Walkthrough | 2026-11-22 | Team | Not Started
4 | Documentation & Testing |  | Team | Not Started
4.1 | Technical Documentation | 2026-12-03 | Musaib / Team | Not Started
4.2 | Bug Tracker | 2026-12-10 | Team | Not Started
4.3 | Issue Log | 2026-12-10 | Team | Not Started
4.4 | Testing Plans | 2026-12-13 | Darima | Not Started
5 | Final Release |  | Team | Not Started
5.1 | Release 1.0 | 2026-12-13 | Team | Not Started
5.2 | Final 1.0 Release Presentation | 2026-12-17 | Team | Not Started
5.3 | Peer Review | 2026-12-17 | Team | Not Started